## Sheet1
Task | Owner | Status | Start date | End date | Notes | Priority | Deliverable
Local Server to host website | Jennifer Marwitz | Not started | 2024-09-02 | 2024-09-09 | Back-End Development | P0
Git Repository | Kaylee Nguyen | In progress | 2024-09-09 | 2024-09-16 | Host Code Database | P1
Simple Homepage w/ Navigation | Victoria Rowe | Not started | 2024-09-09 | 2024-09-16 | Front-End Development | P2
Allocating User Data | Jennifer Marwitz | Not started | 2024-09-16 | 2024-09-30 | Back-End Development | P3
Implement Logic for Generating Course Plans | Natalie Roman | Not started | 2024-09-30 | 2024-10-07 | Back-End Development | P4
Course Plan Validation | Jasmine Lim | Not started | 2024-10-07 | 2024-10-14 | Back-End Development | P5
Uploading Unofficial Transcript | Kaylee Nguyen | Not started | 2024-10-14 | 2024-10-21 | Front-End Development | P6
Major and minor selection | Natalie Roman | Not started | 2024-10-21 | 2024-10-28 | Front-End Development | P7
Summer school, desired hours, and how getting responses from user | Victoria Rowe | Not started | 2024-10-28 | 2024-11-04 | Front-End Development & Back-End Development | P8
Direct Link to Rate my Professor | Cristiana Eagen | Not started | 2024-11-04 | 2024-11-11 | Front-End Development | P9
Generation of schedule based on all factors | Jasmine Lim | Not started | 2024-11-11 | 2024-11-25 | Front-End Development | P10
Final Touches and submit final product | ALL | Not started | 2024-11-11 | 2024-12-01 | Complete before the project deadline | P11
User Authentication and Login | Natalie Roman | Not started |  |  | Front-End Development & Back-End Development | P3
User Interface Enhancements | Natalie Roman | Not started |  |  | Front-End Development | P2